## Sheet1 (hidden)
ID | Description | Step to reproduce | Severity | Type | QA Origional | Find by
|  |  | Fatal , serious, med, cosmetic | business function, code logic, performance, security, GUI, careless | Review, test, inspection , audit
1 | During create Project_Introduction, we have not given criteria about 3 application. Example: - Application are used more - Application of Viet Nam - Application of foreign - Compare to other application, Babycare application has many highlight about what? | 1. Open JSBC_Project_Introduction.docx 2. Review Introduction Category | meidum | Document mistake | review | ChienBD

## DM
Defect ID | Module | Description | Type | Severity | Priority | Status | Assign to | Root Cause | Create by | Created Date | Close date | Refer
1 | JSBC_MeetingMinute | Wrong project name Baby Care Application not Baby Care | Document Mistake | Medium | Medium | Closed | HieuNN |  | ChienBD | 2014-05-15 | 2014-05-15
2 | JSBC_Project Introduction | During create Project_Introduction, we have not given criteria about 3 existed application. Example: - Applications are on top download applications - Application of Viet Nam - Application of foreign - Compare to other application, Babycare application has many highlights about what? | Document Mistake | Medium | Medium | Closed | VuPB |  | ChienBD | 2014-05-19 | 2014-05-19
3 | JSBC_SRS v0.4 | User case is complex, hard to understand. Use wrong symbols | Document Mistake | Medium | Medium | Closed | VuPB |  | ChienBD | 23/5/2014 | 23/5/2014
4 | JSB_SRS v03 | Add login, logout, Change personal information. Add Actor, Pre-condition, function description attribute in user case table | Document Mistake | Medium | Medium | Closed | VuPB |  | VuPB | 22/5/2014 | 22/5/2014
5 | JSBC_SRS, JSBC_Introduction,JSBC_ProjectPlan, JSBC Config management | Use wrong format | Document Format | Medium | Medium | Closed | HieuNN |  | ChienBD | 23/5/2014 | 23/5/2014